## Sheet1
Milestones | Completed | Date Completed
Phase 1: Business Understanding (September 28-30) | TRUE
o Define project (Sept. 28- Sept.28) | TRUE | 2026-09-17
o Define goals (Sept. 28- Sept.28) | TRUE | 2026-09-18
o Identify key stakeholders (Sept. 29- Sept.29) | TRUE | 2026-09-18
o Define success criteria (Sept. 29- Sept.29) | TRUE | 2026-09-21
o Creating a project plan (Sept. 30- Sept.30) | TRUE | 2026-09-21
o Complete the project proposal (Sept. 30- Sept.30) | TRUE | 2026-09-22
Phase 2: Data understanding (October 1-7) | TRUE
o Determining what data is needed to answer the questions (Oct. 1- Oct. 1) | TRUE | 2026-09-23
o Verify data access permissions (Oct. 1- Oct. 1) | TRUE | 2026-09-23
o Gather the data (Oct. 2- Oct. 2) | TRUE | 2026-09-23
o Document data dictionaries and data schema (Oct. 5- Oct. 5) | TRUE | 2026-09-24
o Access data quality and volume (Oct. 6- Oct. 6) | TRUE | 2026-09-24
o Explore the data (Oct. 7- Oct. 7) | TRUE | 9/24-9/25
Phase 3: Data Preparation (October 8-16) | FALSE
o Clean the data (Oct. 8- Oct. 12) | TRUE | 2026-09-25
o Combine data sets (Oct. 13- Oct. 14) | TRUE | 2026-09-25
o Preprocess the data for the ML model (Oct. 15- Oct. 15) | TRUE | 2026-09-29
o Feature engineering (Oct. 16- Oct. 16) | TRUE | 2026-09-29
Phase 4: Modeling (October 19-23) | FALSE
o Establish a baseline model (Oct. 19- Oct. 19) | TRUE | 2026-09-29
Determine the optimal number of clusters | TRUE | 2026-09-28
o Split the data sets (Oct. 19- Oct. 19) | FALSE
o Build and train the model (Oct. 20- Oct. 20) | TRUE | 2026-09-29
Interperate cluster characteristics | TRUE | 2026-09-30
o Hyperparameter tuning and cross-validation (Oct. 21- Oct. 22) | FALSE
o Track the model using W&B (Oct. 20- Oct. 22) | TRUE | 2026-09-29
o Test, evaluate, and interpret the results of the model (Oct. 23- Oct. 23) | TRUE | 2026-10-01
Phase 5: Evaluation (October 26- November 4) | FALSE
o Align technical performance with business impact (Oct. 26- Oct. 26) | TRUE | 2026-09-30
o Evaluate the success of the model and analysis (Oct. 27- Oct. 27) | TRUE | 2026-09-30
o Analyze error and bias (Oct. 28- Oct. 28) | FALSE
o Make any needed corrections (Oct. 30- Nov. 2) | TRUE | 2026-09-30
o Summarize the findings (Nov. 3 -Nov.3) | FALSE
o Determine if additional iterations are needed (Nov. 3 -Nov.3) | FALSE
o Conduct a peer review/code edit (Nov. 4- Nov. 4) | FALSE
Phase 6: Deployment (November 5 -10) | FALSE
o Define deployment architecture (Nov. 5 -Nov. 5) | FALSE
o Draft technical documents (Nov. 5 – Nov. 6) | TRUE | 2026-10-01
o Create data dashboards (Nov. 6 -Nov. 9) | FALSE
o Create the final report (Nov. 9 -Nov. 10) | FALSE
o Share findings with the board (Nov.10 -Nov.10) | FALSE